## support
examples to fill the national dissemination plans - 2 planned activities / month / country
description of planned activity | channel of communication | key message | planned timing | reached target group category | number of reached individuals / organizations | expected impact | source of proof impact | realised activity | channel of communication | key message | realised timing | reached target group category | number of reached individuals / organizations | reached impact | proof of realised activity | proof of realised impact
Facebook post-series (incl. interviews with the target group etc.) | online, Facebook page of the project | the project started, mission of the project: Why is the problem of the project relevant? Who are the people "suffering" from the problem? What do they say? What needs do they express that the partnership wants to respond to? | 2019-12-01 | general public | 400+ | increased awareness about the problem of the project is planning to address | survey of 400 people of the target group at the beginning and at the end of the project (HU 100 people, IT 100 people, RO 100 people, NL 100 people)
Facebook post | online, Facebook page of xxx | the kick-off meeting | 2019-12-01 | general public | 700 | increased competence development (skills, knowledge, attitude, autonomy/responsibility) | survey at the beginning and at the end of the project
meeting of teachers at the school (xxx) | offline, teachers meeting | about the project and the connecting tasks | 2019-12-01 | teachers inside the organization | 18 | changed processes within the organisation
article in the local newspaper | offline, xxx | the aims of the project | 2020-01-01 | local people | 1500 | increased level of happiness within the organisation (healthier climate) | survey at the beginning and at the end of the project
conference presentation | offline, educational conference in xxx | about the project aims and methods | Febr. 2020 | professional stakeholders, teachers | 120
parents' meeting | offline, regular parents meeting in the school | about the project and the students mobilities | Febr. 2020 | parents | 150
school radio announcement | offline, once a week | about the relevant information of the project | continuously from Dec. 2019 until the end of the project | students, teachers | 160
online webinar | online | outcomes that are usable beyond the partnership
Please enter all project level and national level dissemination activities according to the examples above.

## project_level
description of planned activity | channel of communication | key message | planned timing | reached target group category | number of reached individuals / organizations | expected impact | source of proof impact | realised activity | channel of communication | key message | realised timing | reached target group category | number of reached individuals / organizations | reached impact | proof of realised activity | proof of realised impact
targeted FB-campaign (interviews, opinion articles, relevant videos etc.) | FB-page of the project | mission of the project, awareness raising about the key problems targeted by the project | beginning of the project | students' families, students, teachers, general public |  | increased awareness of the target groups about the fact that the problem exists and that this partnership is planning to act upon it | survey at the beginning and at the end of the project

## Hungary
description of planned activity | channel of communication | key message | planned timing | reached target group category | number of reached individuals / organizations | expected impact | source of proof of impact | realised activity | channel of communication | key message | realised timing | reached target group category | number of reached individuals / organizations | reached impact | proof of realised activity | proof of realised impact
Meeting the parents at the school | offline meeting at the school | about the project | 2019-12-01 | parents | 75
Facebook post | online facebook page of the school | about the project | 2019-12-01 | students' families, students, teachers, general public | 586
Facebook post | online facebbok page of the school | about the kick off meeing | 2019-12-01 | students' families, students, teachers, general public | 586
Facebook post | online facebbok page of the school | about the partners | 2020-01-01 | students' families, students, teachers, general public | 586
Facebook post | online facebbok page of the school | about the project | 2020-01-01 | students' families, students, teachers, general public | 600
Facebook post ( 2 ) | online facebook page of the school | about IO1, IO2 | 2020-02-01 | students' families, students, teachers, general public | 600
meeting with the studets | offline, students meeting | about the project | 2020-03-01 | studets | 140
Facebook post | online facebook page of the school | about the project | 2020-03-01 | students' families, students, teachers, general public | 600
Facebook post | online facebook page of the school | about the Spring camp | 2020-04-01 | students' families, students, teachers, general public | 600
Meeting the parents at the school | offline parents meeting | about the Spring camp | 2020-04-01 | parents | 70
Facebook posts ( 2 ) | online facebook page of the school | about Spring camp | 2020-05-01 | students' families, students, teachers, general public | 600
Meeting with the teachers | offline teachers meeting | about the teacher training | 2020-06-01 | teachers | 100
Facebook post | online facebook page of the school | about joint staff meeting | 2020-06-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about the project | 2020-07-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about the Autumn camp | 2020-08-01 | students' families, students, teachers, general public | 600
Meeting parents at the school | offline meeting at the school | about the Autumn camp | 2020-09-01 | parents | 100
Meeting with the teachers | offline meeting at the school | about the Autumn camp | 2020-09-01 | teachers | 100
Facebook posts ( 2 ) | online facebook page of the school | about the Autumn camp,about the 3TPM and life skills | 2020-10-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about the 3TPM and life skills | 2020-11-01 | students' families, students, teachers, general public | 600
Facebook post | online facebook page of the school | about the " Parents guide " | 2020-12-01 | students' families, students, teachers, general public | 600
Facebook post | online facebook page of the school | about the "Training course for teachers" | 2020-12-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about IO3, IO4 | 2021-01-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about the project | 2021-02-01 | students' families, students, teachers, general public | 600
Meeting the parents at the school | offline meeting at the school | about " The parents guide " | 2021-03-01 | parents | 100
Facebook post | online facebook page of the school | about the project | 2021-03-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about 4th TPM | 2020-04-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about 4th TPM | 2021-05-01 | students' families, students, teachers, general public | 600
Meeting the parents at the school | offline meeting at the school | about the project development | 2021-06-01 | parents | 150
Facebook post | online facebook page of the school | about the project development | 2021-06-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about the IO s of the project | 2021-07-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about self-assessment tools for students | 2021-08-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about the fourthcoming multiplier event | 2021-09-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | about 5th TPM | 2021-10-01 | students' families, students, teachers, general public | 600
Facebook posts (2 ) | online facebook page of the school | about multiplier event | 2021-11-01 | students' families, students, teachers, general public | 600
Facebook posts ( 2 ) | online facebook page of the school | the aims of the project | 2021-12-01 | students' families, students, teachers, general public | 600
Facebook posts (7) | online, Facebook page of the project | about project partners | December 2019-January 2020 | general public | 700
Facebook post | online, Facebook page of xxx | about the project | 2019-12-01 | general public | 400
website | online, www.xxx.hu | about the kick-off meeting | 2020-01-01 | general public | 300
website | online, www.xxx.eu | about the kick-off meeting | 2020-01-01 | general public | 200
website | online, www.xxx.eu | about IO1, IO2 | 2020-02-01 | general public | 200
Facebook post | online, Facebook page of the project | about IO1, IO2 | 2020-02-01 | general public | 700
talking of students at the schools | offline, students meeting | about the life-skill | 2020-03-01 | students | 100
article in the local newspaper | offline, xxx | the aims of the project | 2020-03-01 | general public | 30000
conference presentation | offline, educational conference in Szeged | about the project aims and methods | 2020-04-01 | professional stakeholders, teachers | 100
Facebook post | online, Facebook page of the project | about Spring Camp | 2020-04-01 | general public | 700
Facebook post | online, Facebook page of xxx | about Spring Camp | 2020-05-01 | general public | 400
meeting of teachers at the schools | offline, teachers meeting | about the "Training course for teachers" | 2020-05-01 | teachers | 50
Facebook post | online, Facebook page of the project | about Joint staff meeting | 2020-05-01 | general public | 700
website | online, www.xxx.hu | about Spring Camp | 2020-05-01 | general public | 300
website | online, www.xxx.hu | about Joint staff meeting | 2020-05-01 | general public | 300
website | online, www.xxx.eu | about Spring Camp | 2020-05-01 | general public | 200
website | online, www.xxx.eu | about Joint staff meeting | 2020-05-01 | general public | 200
Facebook post | online, Facebook page of xxx | about Joint staff meeting | 2020-06-01 | general public | 400
website | online, www.xxx.eu | about IO1, IO2, IO3 | 2020-06-01 | general public | 200
Facebook post | online, Facebook page of the project | about IO1, IO2, IO3 | 2020-07-01 | general public | 700
website | online, www.xxx.hu | about IO1, IO2, IO3 | 2020-07-01 | general public | 300
meeting of teachers at the schools | offline, teachers meeting | about the "Training course for teachers" | 2020-08-01 | teachers | 50
Facebook post | online, Facebook page of the project | about Autumn Camp | 2020-08-01 | general public | 700
talking of students at the schools | offline, students meeting | about the life-skill | 2020-09-01 | students | 100
Facebook post | online, Facebook page of xxx | about Autumn Camp | 2020-09-01 | general public | 400
website | online, www.xxx.hu | about Autumn Camp | 2020-09-01 | general public | 300
website | online, www.xxx.eu | about Autumn Camp | 2020-09-01 | general public | 200
Facebook post | online, Facebook page of the project | about 3rd TPM | 2020-10-01 | general public | 700
Facebook post | online, Facebook page of xxx | about 3rd TPM | 2020-10-01 | general public | 400
website | online, www.xxx.hu | about 3rd TPM | 2020-10-01 | general public | 300
website | online, www.xxx.eu | about 3rd TPM | 2020-10-01 | general public | 200
website | online, www.xxx.eu | about IO1, IO2, IO3, IO4 | 2020-11-01 | general public | 200
Facebook post | online, Facebook page of the project | about IO1, IO2, IO3, IO4 | 2020-11-01 | general public | 700
meeting of teachers at the schools | offline, teachers meeting | about the "Training course for teachers" | 2020-12-01 | teachers | 50
meeting of parents at the schools | offline, parents meeting | about the "Parents' guide" | 2020-12-01 | parents | 100
website | online, www.xxx.eu | about IO3, IO4 | 2021-01-01 | general public | 200
Facebook post | online, xxx page of the project | about IO3, IO4 | 2021-01-01 | general public | 700
Annual wall calendar | offline, paper-based | with project activities photos | 2021-02-01 | general public
Teacher forum | offline, educational meeting in xxx | about the intellectual outputs | 2021-02-01 | teachers
article in the local newspaper | offline, xxx | the aims of the project | 2021-03-01 | general public | 30000
meeting of parents at the schools | offline, parents meeting | about the "Parents' guide" | 2021-03-01 | parents | 100
Facebook post | online, Facebook page of the project | about 4th TPM | 2021-04-01 | general public | 700
Facebook post | online, Facebook page of xxx | about 4th TPM | 2021-04-01 | general public | 400
website | online, www.xxx.hu | about 4th TPM | 2021-04-01 | general public | 300
website | online, www.xxx.eu | about 4th TPM | 2021-04-01 | general public | 200
conference presentation | offline, educational conference in xxx | about the project aims and methods | 2021-05-01 | professional stakeholders, teachers | 100
Leaflet | offline, paper-based brochure | about Intellectual Outputs | 2021-05-01 | teachers
website | online, www.xxx.eu | about IO3, IO4 | 2021-06-01 | general public | 200
Facebook post | online, Facebook page of the project | about IO3, IO4 | 2021-06-01 | general public | 700
Poster | offline, paper-based | about IO1, IO2, IO3, IO4 | 2021-07-01 | teachers
conference presentation | offline, educational conference in xxx | about the project aims and methods | 2021-08-01 | professional stakeholders, teachers | 100
Photo album | offline, photos | about project activities | 2021-09-01 | participants, stakeholders
Facebook post | online, Facebook page of the project | about 5th TPM | 2021-10-01 | general public | 700
Facebook post | online, Facebook page of xxx | about 5th TPM | 2021-10-01 | general public | 400
website | online, www.xxx.hu | about 5th TPM | 2021-10-01 | general public | 300
website | online, www.xxx.eu | about 5th TPM | 2021-10-01 | general public | 200
website | online, www.xxx.hu | about multiplier event | 2021-11-01 | general public | 300
website | online, www.xxx.eu | about multiplier event | 2021-11-01 | general public | 200
website | online, www.xxx.hu | about multiplier event | 2021-12-01 | general public | 300
website | online, www.xxx.eu | about multiplier event | 2021-12-01 | general public | 200
article in the local newspaper | offline, xxx | the aims of the project | 2021-12-01 | general public | 30000

## Italy
description of planned activity | channel of communication | key message | planned timing | reached target group category | number of reached individuals / organizations | expected impact | source of proof impact | realised activity | channel of communication | key message | realised timing | reached target group category | number of reached individuals / organizations | reached impact | proof of realised activity | proof of realised impact
Open day | off line meeting | Project structure | Dec.2019 | new students' families | 200 people | increased awareness of the target groups about the fact that the problem exists and that this partnership is planning to act upon it | survey at the beginning and at the end of the project
Facebook post | on line Facebook page | project structure | 2019-12-01 | new students' families
Description of the project | School website | project structure and school involvment | 2019-12-01 | teachers, students, families
Description of the project | xxx's Website | Project description and role of xxx (partner organisation) | 2019-12-01 | Social Cooperatives, xxx network, Municipality of Perugia, Informagiovani Service | 1000
Facebook posts | xxx Facebook page | Posts relating to project development and achievements/ milestones | every 2 months on avg. starting Dec 2019 | Social Cooperatives, xxx network, Municipality of Perugia, Informagiovani Service | Page with 1432 followers (currently)
teachers meeting | offline, teachers meeting | project steps | 2020-01-01 | istituto comprensivo teachers | 100 teachers
Facebook posts | online, facebook page of the project | about project partners | 2020-01-01 | teachers, students, families, | 3000
school website | online, school website | about the kick-off meeting | 2020-02-01 | students' families | 2000
Facebook page | online, Facebook page | about the kick-off meeting | 2020-02-01 | Families, population, schools | 3000
teachers' meeting | off-line, teachers' meeting | Spring Camp organization | 2020-03-01 | teachers | 100
parents' meeting | off-line, parents' meeting | Spring Camp organization | 2020-03-01 | teachers and families | 300
website | on-line, school website | about activities to develop life-skills | 2020-04-01 | teachers, families, students | 400
Facebook page | on-line, facebook page | about activities to develop life skills | 2020-04-01 | teachers, families, students | 400
Local newspaper | off-line, article in the local newspaper | activities for Spring festival event | 2020-05-01 | school and local community | 2000
school website | on-line, video | activities for Spring festival event | 2020-05-01 | local community | 2000
facebook post | on-line | Spring camp activities | 2020-06-01 | teachers and families | 300
school website | on-line | Spring camp activities | 2020-06-01 | teachers and families | 300
facebook post | on-line | joint staff meeting | 2020-07-01 | students, families, teachers | 500
school website | on-line | joint staff meeting | 2020-07-01 | students, families, teachers | 500
Facebook page | on-line | project development | 2020-08-01 | community | 1000
school website | on-line | project development | 2020-08-01 | families, teachers | 500
teachers' meeting | off-line | ready for Fall Camp | 2020-09-01 | teachers | 100
parents' meeting | off-line | Ready for fall Camp | 2020-09-01 | families | 100
students' meeting | off-line | activities on life-skills | 2020-10-01 | students | 300
school website | on-line | activities to develop life-skills | 2020-10-01 | community | 1000
teachers' meeting | off-line | teachers' training organization | 2020-11-01 | teachers | 100
facebook page | on-line | focus on IO 1-2 | 2020-11-01 | community | 2000
website | on-line | focus on IO 1-2 | 2020-12-01 | community | 2000
Facebook page | on-line | focus on IO 3-4 | 2021-01-01 | community | 2000
school website | on-line | focus on IO 3-4 | 2021-01-01 | community | 2000
Teachers' meeting | off-line | project development | 2021-02-01 | teachers | 100
parents' meeting | off-line | project development | 2021-02-01 | families | 200
students' meeting | off-line | self assessment tools | 2021-03-01 | students | 300
facebook page | on-line | project activities | 2021-03-01 | local community | 1000
website page | on-line | project activities | 2021-04-01 | local community | 1000
Local newspaper | article in local newspaper | project activities | 2021-04-01 | local community | 1500
Parents' meeting | off-line | life-skills activities | 2021-05-01 | families | 200
teachers' meeting | off-line | life-skills activities | 2021-05-01 | teachers' | 100
facebook page | on-line | life-skills activities | 2021-06-01 | local community | 2000
website page | on-line | life-skills activities | 2021-06-01 | local community | 2000
Local newspaper | article in local newspaper | describe project activities | 2021-07-01 | local community | 2500
Exhibition | off-line | photo gallery | 2021-07-01 | students, families, teachers | 900
brochure | off-line | about IOs | 2021-08-01 | students, families, teachers | 900
facebook page | on-line | about IOs | 2021-08-01 | community | 2000
teachers' meeting | off-line | project development | 2021-09-01 | teachers | 100
families' meeting | off-line | project development | 2021-09-01 | families | 900
Local newspaper | off-line | project aim and dissemination | 2021-10-01 | community | 1000
Facebook page | on-line | lab. activities | 2021-10-01 | community | 1000
website | on-line | students' lab activities | 2021-10-01 | community
teachers' meeting | off-line | multiplier event | 2021-11-01 | teachers | 100
parents' meeting | off-line | multiplier event | 2021-11-01 | Families | 900
Website | on-line | multiplier event | 2021-12-01 | community | 2000
Facebook page | on-line | multipler event | 2021-12-01 | community | 2000

## Romania
description of planned activity | channel of communication | key message | planned timing | reached target group category | number of reached individuals / organizations | expected impact | source of proof of impact | realised activity | channel of communication | key message | realised timing | reached target group category | number of reached individuals / organizations | reached impact | proof of realised activity | proof of realised impact
FB post | online FB page of the school | about the kick-off meeting | 2019-12-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about the kick-off meeting | 2019-12-01 | students' families, students, teachers, general public | 4448
FB post | online FB page of the school | about project partners | 2020-01-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about project partners | 2020-01-01 | students' families, students, teachers, general public | 4448
FB post | online FB page of the school | about IO1, IO2 | 2020-02-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about the project | 2020-02-01 | students' families, students, teachers, general public | 4448
talking of students at the schools | offline, students meeting | about the life-skill | 2020-03-01 | students | 100
article in the school newspaper | offline, SuliRikkancs | about the project | 2020-03-01 | students' families, students, teachers, general public | 450
FB post | online FB page of the school | about the Spring Camp | 2020-04-01 | students' families, students, teachers, general public | 1830
conference presentation | offline, conference in Miercurea Ciuc | about the project aims and methods | 2020-04-01 | professional stakeholders, teachers, higher education representatives | 200
FB post | online, FB page of the school | about Spring Camp | 2020-05-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about Spring Camp | 2020-05-01 | students' families, students, teachers, general public | 4448
FB post | online, FB page of the school | about Joint staff meeting | 2020-06-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about Joint staff meeting | 2020-06-01 | students' families, students, teachers, general public | 1830
teachers’ professional meeting | offline, teachers meeting | about the project | 2020-07-01 | teachers | 300
website | online, www.xxxiskola.ro | about intellectual outputs under development | 2020-07-01 | students' families, students, teachers, general public | 4448
FB post | online, FB page of the school | about Autumn Camp | 2020-08-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about Autumn Camp | 2020-08-01 | students' families, students, teachers, general public | 4448
parents meeting | off line meeting at the school | about the project | 2020-09-01 | parents | 250
meeting of teachers at the schools | offline, teachers meeting | about the Autumn Camp | 2020-09-01 | teachers | 50
talking of students at the schools | offline, students meeting | about life-skills | 2020-10-01 | students | 300
article in the school newspaper | offline, SuliRikkancs | about 3rd TPM | 2020-10-01 | students' families, students, teachers, general public | 450
FB post | online, FB page of the school | about Autumn Camp | 2020-11-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about Autumn Camp | 2020-11-01 | students' families, students, teachers, general public | 4448
meeting of teachers at the schools | offline, teachers meeting | about the "Training course for teachers" | 2020-12-01 | teachers | 50
meeting of parents at the schools | offline, parents meeting | about the "Parents' guide" | 2020-12-01 | parents | 250
FB post | online FB page of the school | about IO1, IO2 | 2021-01-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about IO1, IO2 | 2021-01-01 | students' families, students, teachers, general public | 4448
FB post | online FB page of the school | about IO3, IO4 | 2021-02-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about IO3, IO4 | 2021-02-01 | students' families, students, teachers, general public | 4448
article in the school newspaper | offline, SuliRikkancs | about 4th TPM | 2021-03-01 | students' families, students, teachers, general public | 450
FB post | online, FB page of the school | about 4th TPM | 2021-03-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about 4th TPM | 2021-04-01 | students' families, students, teachers, general public | 4448
article in the local newspaper | offline, Székelyhon | about 4th TPM | 2021-04-01 | general public | 85000
FB post | online FB page of the school | about the project development | 2021-05-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about the project development | 2021-05-01 | students' families, students, teachers, general public | 4448
meeting of parents at the schools | offline, parents meeting | about the project development | 2021-06-01 | parents | 250
meeting of university teachers | offline, teachers meeting | about the project development | 2021-06-01 | university teachers | 25
FB post | online FB page of the school | about the IO s of the project | 2021-07-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about the IO s of the project | 2021-07-01 | students' families, students, teachers, general public | 4448
FB post | online FB page of the school | about the self-assessment tool for students | 2021-08-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about the self-assessment tool for students | 2021-08-01 | students' families, students, teachers, general public | 4448
FB post | online FB page of the school | about the forthcoming multiplier event | 2021-09-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about the forthcoming multiplier event | 2021-09-01 | students' families, students, teachers, general public | 4448
FB post | online, FB page of the school | about 5th TPM | 2021-10-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about 5th TPM | 2021-10-01 | students' families, students, teachers, general public | 4448
FB post | online, FB page of the school | about multiplier event | 2021-11-01 | students' families, students, teachers, general public | 1830
website | online, www.xxxiskola.ro | about multiplier event | 2021-11-01 | students' families, students, teachers, general public | 4448
article in the local newspaper | offline, Székelyhon | about multiplier event | 2021-12-01 | general public | 85000
article in the school newspaper | offline, SuliRikkancs | about multiplier event | 2021-12-01 | students' families, students, teachers, general public | 450

## NL
description of planned activity | channel of communication | key message | planned timing | reached target group category | number of reached individuals / organizations | expected impact | source of proof of impact | realised activity | channel of communication | key message | realised timing | reached target group category | number of reached individuals / organizations | reached impact | proof of realised activity | proof of realised impact
Meeting partners of project | email, drive platform | Introduction, projectplanning | 2 days in dec 2019 | projectpartners | 25
Kick-off meeting in Szeged | A meeting | Planning the project | 2 days in Dec 2019 | projectpartners | 25
Informing all Partners of zzz | By Email, news letter | yyy project | Dec/ Jan 2020 | 5 partners | 30
Partner of zzz Risk Changer | By Email, news letter | yyy project | 2020-01-01 | 150 schools | 300
Partner of zzz stichting CEDgroep Rotterdam | By Email, news letter | yyy Project | 2020-01-01 | 100 Proffesionals in training for teacher | 100
Dalton Apollo 11 De Meern | Meeting | School particitatie school | Meeting dec 2019 | 15 parents, 10 students 6 teachers | 31
website | online, www.yyy.eu | about IO1, IO2 | 2020-02-01 | Partners of zzz general public
Facebook post | online, Facebook page of the project | about IO1, IO2 | 2020-02-01 | partners of zzz general public
website | online, www.yyy.eu | about Spring Camp | 2020-05-01 | general public, Apollo 11
website | online, www.yyy.eu | about IO1, IO2, IO3 | 2020-06-01 | partners of zzz general public
Facebook post | online, Facebook page of the project | about IO1, IO2, IO3 | 2020-07-01 | partners of zzz general public
website | online, www.zzz.nl | about IO1, IO2, IO3 | 2020-07-01 | general public
Facebook post | online, Facebook page of the project | about Autumn Camp | 2020-08-01 | general public
talking of partners of zzz | offline, partners meeting | about the life-skill | 2020-09-01 | partners of zzz
Facebook post | online, Facebook page of the project | about 3rd TPM | 2020-10-01 | general public
Facebook post | online, Facebook page of zzz.nl | about 3rd TPM | 2020-10-01 | general public
website | online, www.zzz.nl | about 3rd TPM | 2020-10-01 | general public
website | online, www.yyy.eu | about 3rd TPM | 2020-10-01 | general public
website | online, www.yyy.eu | about IO1, IO2, IO3, IO4 | 2020-11-01 | general public
Facebook post | online, Facebook page of the project | about IO1, IO2, IO3, IO4 | 2020-11-01 | general public
meeting of parents at the schools | offline, partners meeting | about the "Parents' guide" | 2020-12-01 | partners of zzz
website | online, www.yyy.eu | about IO3, IO4 | 2021-01-01 | general public
Facebook post | online, Facebook page of the project | about IO3, IO4 | 2021-01-01 | general public
Teacher forum | offline, educational meeting in Szeged | about the intellectual outputs | 2021-02-01 | partners of zzz
article in the local newspaper | offline, Garderen | the aims of the project | 2021-03-01 | general public
meeting of partners meeting | offline, partners meeting | about the "Parents' guide" | 2021-03-01 | partners of zzz
Facebook post | online, Facebook page of the project | about 4th TPM | 2021-04-01 | general public
Facebook post | online, Facebook page of zzz.nl | about 4th TPM | 2021-04-01 | general public
website | online, www.zzz.nl | about 4th TPM | 2021-04-01 | general public
website | online, www.yyy.eu | about 4th TPM | 2021-04-01 | general public
website | online, www.yyy.eu | about IO3, IO4 | 2021-06-01 | general public
Facebook post | online, Facebook page of the project | about IO3, IO4 | 2021-06-01 | general public
Poster | offline, paper-based | about IO1, IO2, IO3, IO4 | 2021-07-01 | Office school apollo 11
Photo album | offline, photos | about project activities | 2021-09-01 | participants, stakeholders
Facebook post | online, Facebook page of the project | about 5th TPM | 2021-10-01 | general public
website | online, www.zzz.nl | about 5th TPM | 2021-10-01 | general public
website | online, www.yyy.eu | about 5th TPM | 2021-10-01 | general public
website | online, www.zzz.nl | about multiplier event | 2021-11-01 | general public
website | online, www.yyy.eu | about multiplier event | 2021-11-01 | general public
website | online, www.zzz.nl | about multiplier event | 2021-12-01 | general public
website | online, www.yyy.eu | about multiplier event | 2021-12-01 | general public
article in the local newspaper | offline, Garderen | the aims of the project | 2021-12-01 | general public